## Risk Register
Risk ID | Asset/System | Business Owner | Data Classification | Threat | Vulnerability | Existing Controls | Likelihood (1-5) | Impact (1-5) | Risk Score (=L*I) | Risk Level | Proposed Treatment (Avoid/Reduce/Transfer/Accept) | Proposed Controls | NIST CSF Function (G/I/P/D/R) | Target Date | Status
RR-001 | Customer Web App (SaaS) | App Owner | Confidential | SQL Injection | Insufficient input validation | Parameterized queries, code review | 4 | 5 |  |  | Reduce | WAF rules; CI/CD SAST; secure coding training | Protect/Detect | 2025-08-01 | Open
RR-002 | IdP (SSO/MFA) | IT Sec | Internal | Credential stuffing | Weak password hygiene | MFA enabled | 3 | 4 |  |  | Reduce | Rate limiting; password manager; auth anomaly monitoring | Protect/Detect | 2025-07-15 | Open
RR-003 | Payment Processor | Finance/IT | Restricted | Data exfiltration | Over-permissive S3 bucket policy | S3 default encryption | 2 | 5 |  |  | Transfer | Review cyber insurance; tighten S3 policies; enable access logs | Protect/Detect/Respond | 2025-07-31 | Open
RR-004 | HR Portal | HR Lead | Confidential | Payroll change fraud via phishing | Low awareness / no phishing tests | Email gateway | 3 | 4 |  |  | Reduce | Awareness training + phishing simulations; DMARC | Protect/Detect | 2025-07-20 | Open